## Sheet1
Risk Assessment Matrix
Consequences |  |  |  |  | Increasing Probability
# | Factor | Deductions | Outcome | Severity | Very unlikely | Unlikely | Likely | Very likely
1 | Running out of time and not meeting the requirement of the project. | Work in planned sprints that allocate a cetain amount of time to tasks. Use a kanban style board to visually plan out and keep track of tasks that need creating and completing. Also allows yo to see competed tasks to avoid repeating work that has already been done | Continous progression and improvement of project material and having enough time and flexibilty whilst working on the project without having a negative impact on the quality or functioning of the final product. | 1
2 | Misunderstaning the scope of the project and therefore not meeting the minimum requirements | Refer back to the marking criteria and tailor the tasks set for the project to each criteria point in the mark scheme | The main goal is to meet all the minimum requirements set out in the project brief, and then secondary to that is tomake improvements and go beyond the minimum requirements to give a high quality and fully functioning app with all of the relevant functioanlity integrated into it | 2
3 | Potential risk of cloud computing is that there is always a possibility that user data can be accessed by other people, so without good cloud and data protection, data confidentiality issues may arise. | Using Multi-factor authentication (MFA) for user logins is an effective solution. MFAs require a second verification after a password, for example an email or a verification code on a mobile phone owned by the user. | Maximize security to keep user information safe by using both authorisation and authentication measures. This means we know to the best of our ability who is trying to use the service and for what purpose. | 3 |  | 1
4 | Insufficient QA time to test app for bugs | Set strict deadlines and time period for testing. Ensure enough time is available for testing. | Gain full coverage on unit testing and deploy the app on time as fully functioning and with no bugs. | 4 |  | 3 | 2
5 | Vulnerabilities in data security and safety of data stored in databases. | Ensure that no passwords are pushed onto github and use seret keys where applicable to conceal sensitive information | Adhering to best pratices allows the senstive information to be kept safe and stops unwanted access to information and the application. | 5 |  | 4 | 6
6 | Lack of content knowledge or lack of understanding. | Review material regularly and search online and carry out independent research for answers to any issues before asking trainers for help | Complete understanding of all modules covered and this being reflected in the all aspects of the fundamentals project. | 6 |  | 5